## Sheet1
CSI4142 Physical Design and Data Staging - Project Planning
Deliverable | Team member(s) responsible | Expected completion date | Actual completion date | Estimate time (hours) to complete | Actual time (hours) to complete | Notes (if any)
Create database instance and tables | Junbo Tang | 2021-02-24 | 2021-02-25 | 2 | 3
Staging of Date dimension | Yi Zhao | 2021-02-26 | 2021-03-26 | 1 | 2
Staging of Patient dimension | Yi Zhao | 2021-02-27 | 2021-03-01 | 1 | 1.5
Staging of PHU dimension | Junbo Tang | 2021-02-28 | 2021-03-01 | 1 | 1.5
Staging of Mobility dimension | Junbo Tang | 2021-03-02 | 2021-03-04 | 2 | 3
Staging of Weather dimension | Junbo Tang | 2021-03-03 | 2021-03-04 | 2 | 4
Map PHU, Mobility and Weather dimensions | Yi Zhao | 2021-03-06 | 2021-03-06 | 2 | 3
Staging of Special Measures dimension | Yi Zhao | 2021-03-07 | 2021-03-07 | 3 | 3
Surrogate key pipeline – including role-playing dates | Yi Zhao | 2021-03-07 | 2021-03-07 | 3 | 3
Staging of fact table – including FKs and measures | Junbo Tang | 2021-03-08 | 2021-03-08 | 2 | 3
Data quality handling and reporting | Junbo Tang | 2021-03-08 | 2021-03-09 | 2 | 2
Others - if any